## Main page
Tool for estimating the test effort (concept)
The numbers used in this spreadsheet are examples only, and should only be used at your own risk
Sogeti is in no way responsible for incorrect results using this freeware tool |  | Menu:
|  | Steps |  | Info pages
|  | step 1 |  | Info Work breakdown structure
|  | step 2 |  | Info estimation method per QC
step 3
step 4
step 5 (Result)
Version
| 1.0 | Initial version | R. Baarda, E. Notenboom, G. Hoving, Y. van Zaanen
| 1.1 | English translation | T. Koomen
User manual
Legend for using the tool
Input fields
Output fields
Remarks
Go through steps 1-4 of the tool and give all relevant and necessary information in the intended fields. The estimated test effort is displayed in step 5.
Size
Strategy
Productivity
Test Point Analysis
Estimated test effort

## Step 1
Step 1: Define test strategy and risk class
Menu:
go to step 2
go to main page
Input Strategy
Quality Attribute | Insp RQ | Insp FD | Insp TD | UT | IT | ST | UAT | PAT | Risk class
Connectivity | [7 empty] | i
Continuity | [5 empty] | * |  | i | B
Data controllability | [6 empty] | i
Effectivity | [6 empty] | **
Efficiency | [7 empty] | **
Flexibility | [6 empty] | i
Functionality |  | * | * |  |  | *** | ** |  | A
Infrastructure | [7 empty] | i
Maintainability |  | * | * |  |  |  | i | s | C
Manageability |  | * | * |  |  |  |  | * | C
Performance | [8 empty] | C
Batch | [5 empty] | i |  | *
On-line | [5 empty] | i |  | ***
Portability | [5 empty] | ** |  | ***
Reusability | [5 empty] | i
Security | * | * | * |  |  | *** HB | *** WBS |  | C
Suitability | * | * | * |  |  |  | ** |  | B
Testability
User friendliness |  | * | * |  |  |  | i |  | B

## Step 2
Step 2: System characteristics = test object
Menu:
go to step 3
go to step 1
go to main page
Input |  | Output
System size in FP's | 1000 | Af-factor | 1
Complexity | 6
Frequency of use | 4
Uniformity | 4
User importance (fixed) | 6

## Step 3
Stap 3: Productivity for dynamic testing
Menu:
go to step 4
go to step 2
go to main page
Input |  |  |  | Output
| ST | UAT | PAT |  | ST | FAT | PAT
General |  |  |  | Environmental factor | 0.95238 | 0.95238 | 0.95238
Skill factor/productivity | 1 | 2.1 | 2.2 | Team size etc. | 1.1 | 1.1 | 1.1
Environmental components test mgt infra
Test tools | 2 | 2 | 2
Low level tests | 4 | 4 | 4
Test basis | 6 | 6 | 6
Development environment | 4 | 4 | 4
Test environment | 2 | 2 | 2
Testware | 2 | 2 | 2
Additional factor
Team size | 6 | 6 | 6
Man.mnt & control tools | 4 | 4 | 4
Time box in hours
n.b. only if applicable
| Hours | Remark
Security ST | 100 | <-- Please fill in hours
Security FAT | 0 | <-- N/A
Security PAT | 0 | <-- N/A
Functionality UT | 0 | <-- N/A
Functionality IT | 0 | <-- N/A
for Timeboxing
Time duration dynamic tests
| Hours/day | Remark
Continuity | 6 | <-- Please choose hours/day

## Step 4
Step 4: Estimate productivity data for reviews/inspections
Menu:
go to step 5
go to step 3
go to main page
Remark:
This only requires input for those quality attributes that are subject to reviews/inspections for one or more of
the documents below.
Input variables
| Requirements |  | Func design |  | Techn design
Quality attributes | pages | Productivity | pages | Productivity | pages | Productivity
Connectivity |  | 3 |  | 3 | 16 | 3
Continuity |  | 3 |  | 3 |  | 3
Data controllability |  | 3 |  | 3 |  | 3
effectively |  | 3 |  | 3 |  | 3
efficiency |  | 3 |  | 3 |  | 3
flexibility |  | 3 |  | 3 |  | 3
functionality | 34 | 3 | 350 | 3 |  | 3
Infrastructure |  | 3 |  | 3 |  | 3
maintainability |  | 3 |  | 3 | 15 | 3
manageability | 3 | 3 | 16 | 3 | 16 | 3
performance |  | 3 |  | 3 | 12 | 3
portability |  | 3 |  | 3 |  | 3
Reusability |  | 3 |  | 3 |  | 3
security | 3 | 3 | 16 | 3 | 16 | 3
suitability | 8 | 3 | 17 | 3 |  | 3
testability |  | 3 |  | 3 |  | 3
User friendliness |  | 3 | 6 | 3 |  | 3

## Step 5 (Result)
Step 5: Test estimation in hours
Menu:
go to step 4
go to main page
Remark:
Display fields only!
Quality attributes | Insp RQ | Insp FD | Insp TD | UT | IT | ST | UAT | PAT | Sub total | Risk class
Connectivity | [7 empty] | 44 | 44
Continuity | [5 empty] | 42 | 0 | 44 | 86 | B
Data controllability | [6 empty] | 42 |  | 42
Effectivity | [5 empty] | 0 | 110 | 0 | 110
Efficiency | [7 empty] | 28 | 28
Flexibility | [6 empty] | 42 |  | 42
Functionality |  | 116.6667 | 0 | 0 | 0 | 982.1429 | 1650 | 0 | 2748.8095 | A
Infrastructure | [7 empty] | 44 | 44
Maintainability |  | 0 | 5 |  |  |  | 42 | 70.4 | 117.4 | C
Manageability |  | 5.3333 | 5.3333 |  |  |  |  | 24 | 34.6667 | C
Performance | [8 empty] | 0 | C
Batch | [5 empty] | 10 | 0 | 86.4286 | 96.4286
On-line | [5 empty] | 10 | 0 | 224 | 234
Portability | [5 empty] | 52.381 | 0 | 144.0476 | 196.4286
Reusability | [5 empty] | 20 |  |  | 20
Security | 1 | 5.3333 | 5.3333 |  |  | 100 | 80 | 0 | 191.6667 | C
Suitability | 2.6667 | 5.6667 | 0 |  |  | 0 | 110 | 0 | 118.3333 | B
Testability | [8 empty] | 0
User friendliness |  | 2 | 0 |  |  | 0 | 42 | 0 | 44 | B
Total | 3.6667 | 135 | 15.6667 | 0 | 0 | 1216.5238 | 2118 | 708.8762 | 4197.7333

## Info WBS
Ervaringscijfers Work Breakdown Structure
Menu:
go to main page
Quality attribute | Plan | Prepare | Execute | Hours total
Manageability | 4 | 8 | 12 | 24
Security | 16 | 16 | 48 | 80
Portability | 4 | 18 | 16 | 38
Efficiency | 4 | 12 | 12 | 28
Performance (*) | 40 | 32 | 120 | 192
Performance (**) | 40 | 48 | 120 | 208
Performance (***) | 40 | 64 | 120 | 224
User friendliness (*) | 14 | 30 | 26 | 70
User friendliness(**) | 20 | 38 | 42 | 100
User friendliness (***) | 26 | 52 | 52 | 130
Suitability (***) | 70 | 140 | 140 | 350

## Tijdelijk Masterbegroting (hidden)
| ST | FAT | PAT
Uren Performance Batch | #REF! | 0 | 0
Uren Performance Online | 0 | 0 | 0

## Info estimation method
Estimation method per quality attribute
Menu:
go to main page
Quality attribute | Inspection | Static test | UT | IT | Implicit | Dynamic | Dynamic | Dynamic
Intensity -> | see step4 |  |  |  | testing | * | ** | ***
Connectivity |  | TPA-S | - | - | TPA-I | - | - | -
Continuity |  | TPA-S | - | - | TPA-I | Timebox (week) | Timebox (month) | Timebox (quarter)
Data controllability |  | TPA-S | - | - | TPA-I | - | - | -
effectively |  | TPA-S | - | - | TPA-I | TPA | TPA | WBS
efficiency |  | TPA-S | - | - | TPA-I | - | WBS | -
flexibility |  | TPA-S | - | - | TPA-I | - | - | -
functionality |  | TPA-S | Hour box | Hour box | TPA-I | TPA | TPA | TPA
Infrastructure |  | TPA-S | - | - | TPA-I | - | - | -
maintainability |  | TPA-S | - | - | TPA-I | - | - | -
Manageability |  | TPA-S | - | - | TPA-I | WBS | - | -
performance |  | TPA-S | - | - | TPA-I | WBS | WBS | WBS
Batch |  | - | - | - | - | TPA | TPA | TPA
On-line |  | - | - | - | - | WBS | WBS | WBS
portability |  | TPA-S | - | - | TPA-I | WBS | TPA | TPA
Reusability |  | TPA-S | - | - | TPA-I | - | - | -
security |  | TPA-S | - | - | TPA-I | TPA | TPA | WBS
suitability |  | TPA-S | - | - | TPA-I | TPA | TPA | TPA
testability |  | TPA-S | - | - | TPA-I | - | - | -
User friendliness |  | TPA-S | - | - | TPA-I | WBS | WBS | WBS